## Test Plan Template
Test Plan Template
Test Plan Identifier: |  |  | YOYTUBE-AUTO-01
Introduction: |  |  | This test plan covers the automation of YouTube using Selenium. It tests the ability to search for a video, play it, pause after 20 seconds, scroll to comments, scroll back to top, and resume playback.
Objectives: |  |  | The objective is to validate the automated workflow for interacting with YouTube’s search and video interface as a guest user.
Test Scope: |  |  | Scope includes search, play, pause, scroll to comments, scroll up, and resume.
Date: 10/12/24 |  |  | 2025-06-27
Test Items | Features to be Tested | Features Not to be Tested | Test Environment & Tools | Resources | Test Types | Test Strategy and Approach | Entry Criteria | Exit Criteria | Deliverables | Start Date | End Date | Assigned to | Risks and Contingencies | Notes
Youtube Automation test | Search functionality | Login | Selenium WebDriver,Python 3, ChromeDriver, macOS | Selenium WebDriver,Python 3, ChromeDriver, macOS | Functional, UI | Launch Chrome browser using Selenium and navigate to https://www.youtube.com. Check if the search bar appears. | Selenium and ChromeDriver installed. Internet connection stable | YouTube homepage loads and search bar is visible. | Screenshot of homepage, log: "Homepage loaded" | 2025-06-14 | 2025-06-19 | Thaw Hein | YouTube server may be down; DNS issue; search bar element may change | Always wait at least 3 seconds after page load
| Play video | Liking | Selenium WebDriver,Python 3, ChromeDriver, macOS | Selenium WebDriver,Python 3, ChromeDriver, macOS | Functional, UI | Locate the search input field, input “no more lies”, press Enter, and verify results page loads by checking for video thumbnails. | YouTube homepage is fully loaded with search field accessible. | Search results for “no more lies” are shown. | Screenshot of results page | 2025-06-15 | 2025-06-20 | Thaw Hein | Element name or XPath may change if YouTube updates layout | Use try/except for fallback locator strategy
| Pause after 20s | disliking | Selenium WebDriver,Python 3, ChromeDriver, macOS | Selenium WebDriver,Python 3, ChromeDriver, macOS | Functional | Use XPath to locate the first video thumbnail and click it. Validate by checking if video page opens and playback starts. | Search results are shown with video thumbnails. | First video page opens and video auto-plays. | Screenshot of video page | 2025-06-16 | 2025-06-21 | Thaw Hein | If ad plays, it may delay actual video; page load timeout possible | Use WebDriverWait for more reliable loading
| Scroll to comments | Comments | Selenium WebDriver,Python 3, ChromeDriver, macOS | Selenium WebDriver,Python 3, ChromeDriver, macOS | Functional | Wait 20 seconds, then locate the pause button using its class and click it. Confirm by visually checking video is paused. | Video is playing. Timer has reached at least 20 seconds. | Video playback is paused. | Screenshot of paused video | 2025-06-17 | 2025-06-22 | Thaw Hein | Pause button class might not be available during ad; might misclick | Use delay to skip ads, check player state
| Scroll to top | Uploads | Selenium WebDriver,Python 3, ChromeDriver, macOS | Selenium WebDriver,Python 3, ChromeDriver, macOS | UI, Interaction | Wait 5 seconds after pausing, then scroll down using execute_script to 90% of page. Confirm by checking for comment section presence. | Video is paused. Page is stable and ready for scrolling. | Comments section is visible on screen. | Screenshot of visible comments | 2025-06-18 | 2025-06-23 | Thaw Hein | Comments might take time to load depending on connection; layout may vary | Use execute_script in 2 scroll phases
| Resume play |  | Selenium WebDriver,Python 3, ChromeDriver, macOS | Selenium WebDriver,Python 3, ChromeDriver, macOS | Functional, UI | Scroll back to top using JavaScript, then locate play button and click it. Confirm video resumes by checking the play state. | Comments have been scrolled into view and video is paused. | Page scrolls to top, and video resumes playing. | Screenshot and log after resume | 2025-06-19 | 2025-06-24 | Thaw Hein | Button click might fail if ad or overlay appears; scroll may not reset fully | Scroll twice if needed; use visibility checks
Test Plan Team | [12 empty] | Related Free Templates
Name |  |  | Role |  | Responsibilities
Thaw Hein |  |  | Test Manager |  |  |  | Oversee test planning, scheduling, and final delivery. Approve test strategy. | [5 empty] | Gantt Chart Template
Thaw Hein |  |  | Automation Tester |  |  |  | Design, implement, and run Selenium test scripts. Maintain test automation flow. | [5 empty] | Dashboard Template
Thaw Hein |  |  | Manual Tester |  |  |  | Manually validate test steps, record actual results, and help verify edge cases. | [5 empty] | Task Tracker Template
Thaw Hein |  |  | UX Tester |  |  |  | Evaluate UI/UX elements (e.g., visibility, scroll behavior), and report usability issues.